## Scope, Timeline, and Budget
Project Title:
Recipient Name:
FAIN #:
Project POCs:
Name | Title | Email | Phone | Project Role
Project Scope/Statement of Work—Provide 3 or 4 sentences on the scope of project work.
Project Scope/Statement of Work : |  |  |  |  | Project Budget
Project Goals |  |  |  |  | Object Class Categories
Goal #1: Provide benefits to the community through transportation projects. |  |  |  |  | a. Personnel
Goal #2: Increase grant recipient's capacity, knowledge, and skills to execute transportation projects. |  |  |  |  | b. Fringe Benefits
Goal #3: Engage, educate, and listen to the community throughout the project planning process. |  |  |  |  | c. Travel
Goal #4: Advance the transformational project(s) closer to delivery. |  |  |  |  | d. Equipment
Goal #1 | Timeline |  |  |  | e. Supplies
Metrics | Start Date | Due Date | Duration |  | f. Contractual
1.1 |  |  |  |  | g. Construction
1.2 |  |  |  |  | h. Other/Training
Goal #2 | Timeline |  |  |  | i. Total Direct Charges (sum of 6a-6h)
Metrics | Start Date | Due Date | Duration |  | j. Indirect Charges
2.1 |  |  |  |  | k. Totals
2.2
Goal #3 | Timeline
Metrics | Start Date | Due Date | Duration
3.1
3.2
Goal #4: | Timeline
Metrics | Start Date | Due Date | Duration
4.1
4.2

## Risk Management Plan
RISK MANAGEMENT PLAN
Directions: Create a risk registry to identify project risks. For each risk please include information on:
1. Assessment (how could the risk impact the project, the probability of that impact, and the response strategy)
2. Monitoring Process
3. Assignment of Risk Roles and Responsibilities
RISK ID | RISK DESCRIPTION | LIKELIHOOD | IMPACT | RESPONSE STRATEGY | MITIGATE ACTIONS | OWNER
LEGEND
RISK ID | Name of risk
RISK DESCRIPTION | Please provide a description of the identififed risk.
LIKELIHOOD | Scale: Yes or No
IMPACT | Scale: High, Medium, or Low
RESPONSE STRATEGY | Please state your potential response strategy to successfully respond to the identified risk.
MITIGATION ACTIONS | Please state your potential mitigation action(s) to successfully resolve/mitigate the identified risk.
OWNER | Please identify and assign a point of contact to each Risk ID listed above.

## Example (Scope, Timeline, Bdgt)
Project Title: Apple Street Roadway Project
Recipient Name: Apple County, ME
FAIN #: XXXXXX
Project POCs: John Doe and Jane Smith
Name | Title | Email | Phone | Project Role
Jane Smith | City Manager | jsmith@email.com | 555-555-5550 | Project Manager
John Doe | City Engineer | jdoe@email.com | 555-555-5551 | Resident Engineer
Project Scope/Statement of Work—Provide 3 or 4 sentences on the scope of project work.
Project Scope/Statement of Work : Preliminary engineering study, cost estimating, and preliminary environmental assessment of Apple Street to identify needed safety improvements to reduce the number of roadway crashes and fatalities. Proposed benefits include increased safety for commuter and truck traffic along Apple Street's heavly traveled roadway. |  |  |  |  | Project Budget
Project Goals |  |  |  |  | Object Class Categories
Goal #1: Provide benefits to the community through transportation projects. |  |  |  |  | a. Personnel | $ -
Goal #2: Increase grant recipient's capacity, knowledge, and skills to execute transportation projects. |  |  |  |  | b. Fringe Benefits | $ -
Goal #3: Engage, educate, and listen to the community throughout the project planning process. |  |  |  |  | c. Travel | $ -
Goal #4: Advance the transformational project(s) closer to delivery. |  |  |  |  | d. Equipment | $ -
Goal #1 | Timeline |  |  |  | e. Supplies | $ -
Metrics | Start Date | Due Date | Duration |  | f. Contractual | 1390000
1.1 Utilize the City's Public Information Officer to disseminate information via our social media platforms and press releases to increase awareness on safety measures that reduce traffic fatalities and major injuries. | 2027-02-01 | 2028-02-01 | 12 months |  | g. Construction | $ -
1.2 Increase collaboration and coordination among relevant partners to achieve goals of reducing the number of roadway crashes and fatalities on Apple Street. | 2027-03-01 | 2029-08-01 | 29 months |  | h. Other/Training | $ -
Goal #2 | Timeline |  |  |  | i. Total Direct Charges (sum of 6a-6h) | 0
Metrics | Start Date | Due Date | Duration |  | j. Indirect Charges | 110000
2.1 Procure and onboard a consultant with an expertise in corridor analysis of roadway safety countermeasures. | 2026-09-01 | 2027-02-01 | 5 months |  | k. Totals | 1500000
2.2 Participate in three (3) workshops/webinars related to federal processes, project development requirements, and other topics to expand staff knowledge/skills related to this project. | 2026-09-01 | 2029-09-01 | 36 months
Goal #3 | Timeline
Metrics | Start Date | Due Date | Duration
3.1 Host community meetings and workshops virtually and in locations convenient to Apple Street travelers to maximize community input. | 2027-03-01 | 2027-10-01 | 7 months
3.2 Develop and update an Apple Street corridor website with an emphasis on safety countermeasures. | 2027-03-01 | 2029-09-01 | 30 months
Goal #4: | Timeline
Metrics | Start Date | Due Date | Duration
4.1 Develop an Existing Conditions Analysis. | 2027-03-01 | 2027-06-01 | 3 months
4.2Develop Financing Gap Analysis and Strategic Plan. | 2027-06-01 | 2027-10-01 | 4 months
4.3 Complete Preliminary Engineering Study | 2028-04-01 | 2029-08-01 | 16 months
4.4 Complete Preliminary Environmental Assessment | 2027-10-01 | 2028-04-01 | 6 months

## Example (Risk Management Plan)
RISK MANAGEMENT PLAN
Directions: Create a risk registry to identify project risks. For each risk please include information on:
1. Assessment (how could the risk impact the project, the probability of that impact, and the response strategy)
2. Monitoring Process
3. Assignment of Risk Roles and Responsibilities
RISK ID | RISK DESCRIPTION | LIKELIHOOD | IMPACT | RESPONSE STRATEGY | MITIGATE ACTIONS | OWNER
Lack of Internal Management Capacity | Apple County has a number of critical projects under development, which reduces the availability of City staff to complete management tasks. | Yes | High | The County will proactively and consistently check-in with project POCs to assess availability in completing management tasks. | Apple County has support from Orange, Inc.—an on-staff consultant—who has worked extensively with the County for years, and will provide support, as needed, on this project. | Jane Smith
LEGEND
RISK ID | Name of risk
RISK DESCRIPTION | Please provide a description of the identififed risk.
LIKELIHOOD | Scale: Yes or No
IMPACT | Scale: High, Medium, or Low
RESPONSE STRATEGY | Please state your potential response strategy to successfully respond to the identified risk.
MITIGATION ACTIONS | Please state your potential mitigation action(s) to successfully resolve/mitigate the identified risk.
OWNER | Please identify and assign a point of contact to each Risk ID listed above.