## TOC
Innovative Finance and Asset Concession (IFAC) Grant Program
Project Magement Plan & Federal Financial Compliance Template
Workbook Directory
Sheet Name | Description | Interactive Link
Project Budget | Integrated budget worksheet containing task-level entries, dropdown category tagging, and automatic federal Object Class Category totals. | Go to Sheet →
Project Schedule | Project milestones and task timeline schedule detailing expected performance metrics and durations. | Go to Sheet →
Risk Registry | Dynamic risk management register to track, assess, and monitor project risks and mitigation owners. | Go to Sheet →
Formatting Legend & Key
Cell Style | Type of Cell | Description / User Guideline
EDITABLE INPUT | Input Cell | Shaded in light blue. This is a user-editable field for inputs, assumptions, and dates.
AUTOMATED FORMULA | Output Cell | Shaded in light green. Do not edit. This contains spreadsheet formulas that calculate automatically.
DYNAMIC BOUNDARY | Zebra Striped Cell | Alternating light blue-gray shading. Active table boundaries expand as information is typed.
SUMMARY / TOTALS | Totals & Subtotals | Shaded in dark blue or light gray. Summarizes data across tasks or categories.

## Project Budget
Project Management Plan Budget
Innovative Finance and Asset Concession (IFAC) Grant Program
Project Administrative Metadata |  |  |  |  | Project Budget Object Class Categories
| Project Title: | Apple Street Roadway Project |  |  | Object Class | IFAC Grant Costs | Other Funding | Totals
| FAIN #: | 69A6212XXXXXX |  |  | a. Personnel | 20000 | 0 | 20000
| IFAC Federal Award Amount: | 1250000 |  |  | b. Fringe Benefits | 0 | 0 | 0
| Cost Share (Match): | 250000 |  |  | c. Travel | 0 | 0 | 0
| Other Funding: | 0 |  |  | d. Equipment | 0 | 0 | 0
| Total Project Funding: | 1500000 |  |  | e. Supplies | 0 | 0 | 0
| Indirect Cost Rate: | 7.3% |  |  | f. Contractual | 75000 | 0 | 75000
| NICRA Submission Date: | 2025-09-01 |  |  | h. Other/Training | 0 | 0 | 0
[5 empty] | i. Total Direct Charges | 95000 | 0 | 95000
Cost Summary |  |  |  |  | j. Indirect Charges | 6935 | 0 | 6935
| Staff Type / Allocation | Total Cost |  |  | k. Totals | 101935 | 0 | 101935
| IFAC Internal Staff | 70000
| IFAC External Advisors | 25000
| IFAC Indirect Charges | 6935
| Other Funding | 0
| Total Allocated Costs | 101935
Project Cost Breakdown (Task & Cost Element Level)
Tasks/Cost Elements are categorized using standard federal budget object classes. Construction is unallowable under IFAC.
Milestones / Tasks |  |  | Budget Object Class Category | Internal Staff | External Advisors | Total IFAC Costs | Other Funding | All Funding Total
Procure Consultant - SOW Development & RFP drafting |  |  | Contractual | 50000 | 0 | 50000 | 0 | 50000
Public Outreach - Internal Staff Hours |  |  | Personnel | 20000 | 0 | 20000 | 0 | 20000
Public Outreach - External Advisory Consultant |  |  | Contractual | 0 | 25000 | 25000 | 0 | 25000
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
Grand Totals |  |  |  | 70000 | 25000 | 95000 | 0 | 95000
Note on H15: Formula-based default. Overwrite with actual negotiated NICRA dollar amount if needed.
Note on I15: Formula-based default. Overwrite with actual negotiated NICRA dollar amount if needed.

## Project Schedule
Project Management Plan Timeline & Milestone Schedule
Innovative Finance and Asset Concession (IFAC) Grant Program
Project Start Date: | 2026-09-01
Estimated Project End Date: | 2029-08-31
IFAC Federal Grant Allocation: | 1250000
[7 empty] | 2026-07-01 | 2026-10-01 | 2027-01-01 | 2027-04-01 | 2027-07-01 | 2027-10-01 | 2028-01-01 | 2028-04-01 | 2028-07-01 | 2028-10-01 | 2029-01-01 | 2029-04-01 | 2029-07-01 | 2029-10-01 | 2030-01-01 | 2030-04-01 | 2030-07-01 | 2030-10-01 | 2031-01-01 | 2031-04-01 | 2031-07-01 | 2031-10-01 | 2032-01-01 | 2032-04-01
Tasks and Progress Registry | [6 empty] | 2026-09-30 | 2026-12-31 | 2027-03-31 | 2027-06-30 | 2027-09-30 | 2027-12-31 | 2028-03-31 | 2028-06-30 | 2028-09-30 | 2028-12-31 | 2029-03-31 | 2029-06-30 | 2029-09-30 | 2029-12-31 | 2030-03-31 | 2030-06-30 | 2030-09-30 | 2030-12-31 | 2031-03-31 | 2031-06-30 | 2031-09-30 | 2031-12-31 | 2032-03-31 | 2032-06-30
Milestone Group | Tasks and SOW Scope Elements | Cost Estimate | Progress % | Start Date | Due Date | Duration (Months) | 2026-09-30: FY26 Q4 Jul-Sep26; 2026-12-31: FY27 Q1 Oct-Dec26; 2027-03-31: FY27 Q2 Jan-Mar27; 2027-06-30: FY27 Q3 Apr-Jun27; 2027-09-30: FY27 Q4 Jul-Sep27; 2027-12-31: FY28 Q1 Oct-Dec27; 2028-03-31: FY28 Q2 Jan-Mar28; 2028-06-30: FY28 Q3 Apr-Jun28; 2028-09-30: FY28 Q4 Jul-Sep28; 2028-12-31: FY29 Q1 Oct-Dec28; 2029-03-31: FY29 Q2 Jan-Mar29; 2029-06-30: FY29 Q3 Apr-Jun29; 2029-09-30: FY29 Q4 Jul-Sep29
Procure Consultant | Develop RFP | 10000 | 40% | 2026-09-12 | 2026-12-01 | 2.6 | bar: 2026-09-30 to 2026-12-31
Procure Consultant | Send RFP to Bureau for Review | 5000 | 50% | 2026-12-01 | 2027-01-31 | 2 | bar: 2026-12-31 to 2027-03-31
Procure Consultant | Advertise RFP | 5000 | 60% | 2027-02-01 | 2027-03-31 | 1.9 | bar: 2027-03-31
Procure Consultant | Short Selection | 5000 | 60% | 2027-04-01 | 2027-05-15 | 1.4 | bar: 2027-06-30
Procure Consultant | Execute Contract | 25000 | 20% | 2027-05-16 | 2027-07-31 | 2.5 | bar: 2027-06-30 to 2027-09-30
Procure Consultant | Issue Task Order | 0 | 0% | 2027-08-01 | 2027-08-15 | 0.5 | bar: 2027-09-30
Public Outreach | Prepare materials | 15000 | 0% | 2027-09-01 | 2027-11-30 | 3 | bar: 2027-09-30 to 2027-12-31
Public Outreach | Public Notification | 10000 | 0% | 2027-12-01 | 2028-02-29 | 3 | bar: 2027-12-31 to 2028-03-31
Public Outreach | Review Comments & Incorporate feedback | 20000 | 0% | 2028-03-01 | 2028-05-31 | 3 | bar: 2028-03-31 to 2028-06-30
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0
|  | 0 | 0% |  |  | 0

## Risk Registry
Project Risk Management Registry
Innovative Finance and Asset Concession (IFAC) Grant Program
Risk ID | Risk Description | Cause of Risk | Primary Effect | Effect Description | Likelihood | Impact | Response Strategy | Response Actions | Responsible Entity | Monitoring Frequency | Last Review Date | Status
1 | Consultant Onboarding Delays | Insufficient proposals for specialized advisory services | Time | Delay in procurement milestones and corridor analysis | Low - Unlikely (<30%) | Medium - 3 - 6 month delay | Threat - Mitigate | Design RFP to target wide advisor network and host pre-proposal meetings | City Project Manager | Monthly | 2026-09-01 | Active
2 | Public Opposition to Asset Concessions | Misunderstanding of public-private partnership contract terms | Reputation | Local community backlash and political challenges | Medium - Possible (30-70%) | High - >6 month delay | Threat - Mitigate | Create open stakeholder forums, distribute simplified brochures, explain benefits | Public Relations Lead | Bi-Weekly | 2026-09-01 | Active