## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | Transportation
| Week End Date: | 2009-03-27
| Submitter Name: | Lana Hurdle
| Submitter Contact Info: | 202-366-9191
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 69 | 1304 | 2009/2010 | Facilities and Equipment, Recovery Act | 200000000 | 0 | 0
2 | 69 | 1306 | 2009/2010 | Grants-in-aid for Airports, Recovery Act | 1100000000 | 4188392 | 0
3 | 69 | 0504 | 2009/2010 | Highway Infrastructure Investment, Recovery Act | 27460000000 | 3404218380.23 | 1642188.17
4 | 69 | 0504 | 2009/2012 | Highway Infrastructure Investment, Recovery Act | 40000000 | 13987.77 | 3405.17
5 | 69 | 0718 | 2009/2014 | Capital Assistance for High Speed Rail Corridors, Recovery Act | 20000000 | 0 | 0
6 | 69 | 0724 | 2009/2010 | Capital Grants to the National Railroad Passenger Corporation, Recovery Act | 1295000000 | 1288536000 | 11000
7 | 69 | 0724 | 2009/2013 | Capital Grants to the National Railroad Passenger Corporation, Recovery Act | 5000000 | 5000000 | 0
8 | 69 | 0718 | 2009/2012 | Capital Assistance for High Speed Rail Corridors, Recovery Act | 7980000000 | 0 | 0
9 | 69 | 1133 | 2009/2010 | Capital Investment Grants, Recovery Act | 742500000 | 0 | 0
10 | 69 | 1102 | 2009/2010 | Fixed Guideway Infrastructure Investment, Recovery Act | 742500000 | 0 | 0
11 | 69 | 1101 | 2009/2010 | Transit Capital Assistance, Recovery Act | 6850700000 | 46339403 | 0
12 | 69 | 1101 | 2009/2012 | Transit Capital Assistance, Recovery Act | 49300000 | 0 | 0
13 | 69 | 1133 | 2009/2012 | Capital Investment Grants, Recovery Act | 7500000 | 0 | 0
14 | 69 | 1102 | 2009/2012 | Fixed Guideway Infrastructure Investment, Recovery Act | 7500000 | 0 | 0
15 | 69 | 1749 | 2009/2010 | Operations and Training, Recovery Act | 0 | 0 | 0
16 | 69 | 1771 | 2009/2010 | Assistance to Small Shipyards, Recovery Act | 100000000 | 0 | 0
17 | 69 | 0131 | 2009/2013 | Salaries and Expenses, Recovery Act | 20000000 | 0 | 0
18 | 69 | 0106 | 2009/2011 | Supp Disc Grants for Natl Surface Transport System, Recovery Act | 1500000000 | 0 | 0
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
No. | Weekly Update Report Data (sheet 2 of 2)
| Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | As of March 26, FAA has identified nearly $990 million of specific Recovery Act airport projects (92 percent of available total funding). Of that amount, $885 million has been forwarded to the Department, and $451 million has completed the Congressional notification process. | During the week of March 30, FHWA will issue a solicitation for applications for the ferry boat discretionary program.
2
3 | On March 26th, Secretary LaHood announced more than $28 million for Arizona airports under the recently enacted American Recovery and Reinvestment Act (ARRA), including a $10.5 million grant for taxiway rehabilitation at the heavily traveled Phoenix Sky Harbor International Airport. Other Arizona airports that will receive funding include: Tucson International Airport will receive $1.85 million for installing new security equipment, Sierra Vista Municipal Airport in, Sierra Vista, Arizona, will receive $6 million to rehabilitate Runway 12/30, Kingman Airport in Kingman Arizona will receive $5 million to rehabilitate aircraft parking aprons, Taylor Municipal Airport in Taylor Arizona will receive $3.5 million to rehabilitate a runway, Avi Suquilla Airport in Parker, Arizona will receive $1.8 million to rehabilitate two taxiways. | FHWA will finalize the risk management plan for implementation and oversight of ARRA projects and funding.
4
5 | FAA made its first ARRA grant award (obligation) on March 23, when a $4.2 million airport grant was issued to Omaha, NE for Runway Rehabilitation. | On March 31, the Office of Federal Lands Highway will host an ARRA reporting requirements presentation with representatives from the National Park Service, the Fish and Wildlife Service, the Forest Service, the Bureau of Land Management, and the Department of Defense.
6
7 | FAA conducted a public outreach session at the International Aviation Symposium in Phoenix, AZ on March 26-27. | FHWA will allocate Federal Lands Highway Program funding, including the remaining balance ($5.2 million) of Refuge Roads funds, on March 30, and Indian Reservation Roads funds and Park Roads and Parkways funds in early April.
8
9 | On March 23rd, FTA published the $17 million Tribal Transit Program notice in the Federal Register. | The first meeting of the DOT Grants Executive Board will be held on April 6th. The Board will focus on risk management and vulnerabilities for all DOT financial assistance programs under ARRA.
10
11 | On March 24th, FTA published the $100 million Transit Investments for Greenhouse Gas and Energy Reduction notice in the Federal Register. Proposals will be due May 22nd. | FRA will circulate within FRA the internal draft of the strategic plan for high-speed rail and intercity passenger rail grant programs. Will complete DOT and OMB review by third week of April to meet Congressional deadline.
12
13 | On March 27th, Secretary LaHood announced $36 million in ARRA funds for the Central Phoenix/East Valley Light Rail Project. The ARRA funds will help to complete the rail line and allow Valley Metro to begin work on the extension, which is expected to create 10,000 jobs over the life of the project. | Efforts are underway to identify a potential event for May 9th in conjunction with “Train Day.” This date commemorates the day the last spike was driven in connecting the First Transcontinental Railroad.
14
15 | As of March 27th, 35 states have obligated $3.4 billion on nearly 999 projects, more than 10% of apportioned funds. | Efforts are underway to identify a potential June 29th event marking the anniversary of President Eisenhower signing the Federal-aid Highway Act of 1956, the start of the interstate highway system.
16
17 | On March 24, senior FHWA officials met with Inter Tribal Council of Arizona (ITCA) to present information and answer questions regarding ARRA efforts. | With the release of the Federal Register notice, FTA anticipates a number of events related to the allocation of the Capital Investment Grants (New Starts and Small Starts).
18
19 | On March 25, FHWA met with Department of Homeland Security staff from the Customs and Border Patrol and local officials regarding Customs Border Patrol -owned land port-of-entry projects that are funded under ARRA. Future meetings are planned with impacted States. | FTA is coordinating with the Office of the Secretary regarding possible sites for ARRA related events during the Secretary's week-long visit beginning April 13th to ARRA funded projects in several States.
20
21 | FAA has identified five key sites for Heating, Ventilation, and Air Conditioning equipment replacements: Washington Reagan National Airport; Dulles International; Baltimore Washington International; Manassas, VA Airport; and Camp Springs, Maryland (Andrews Air Force Base). | On April 1, FTA will host a workshop for regional and headquarters staff to enhance knowledge of ARRA programs, requirements, grant development and implementation, and monitoring.
22
23 | On March 26th, DOT participated in a webinar hosted by the American Council of Engineering (ACEC). This was one in a series of web seminars for their members on the implementation of the economic stimulus package. | DOT is developing a system to incorporate GIS data to map projects by location, state, type, and congressional district so that the public can see where ARRA projects are located.
24
25 | On March 27th, FTA participated in a webinar hosted by the American Public Transportation Association (APTA). The webinar provided APTA members with up-to-date ARRA related information and a forum to have their questions answered. | DOT launched an initiative to improve the Department’s responsiveness to state and locality single audit findings. Guidance will be issued in early April that will revise procedures and clarify accountability for action.
26
27 | Staff is fielding an average of 30 inquiries per day from stakeholders, regarding the Small Shipyard Grants program and proposed projects. | DOT Office of General Counsel has drafted a memorandum and forms on the requirements for transparency of communications with registered lobbyists as outlined in the President’s Memorandum, issued March 20, 2009. Will finalize memo and forms the first week of April.
28
29 | MARAD has received five Small Shipyard Grant applications thus far, ranging from $1 million to $18 million. Deadline is April 20th. | A Town Hall Training Workshop on ARRA for DOT staff will take place at the week of April 13th . This training is designed for staff below the management level that may be tasked with implementation tasks yet may not fully understand the special requirements in ARRA.
30
31 | DOT has established a help desk to handle incoming calls on ARRA. Statistics on the calls handled for the month of March - week of March 9 – 13th (24 calls), week of March 16 – 20th (31 calls) and week of March 23 – 27th (73 calls). | OST is coordinating the risk management plan for all DOT programs. DOT developed a risk assessment questionnaire that OMB adopted for government-wide use. DOT risk management training will be held on April 1st. Throughout the months of April and May OST will work with Operating Administrations to complete risk assessment questionnaire and risk profile template, develop a risk mitigation and strategy and complete testing and validation of the information.
32
33 | On March 27, Secretary LaHood announced more than $229 million for aviation infrastructure under ARRA. The following states and territories will receive ARRA aviation grants: Alaska, Alabama, American Samoa, Arizona, California, Colorado, Connecticut, Florida, Georgia, Guam, Hawaii, Iowa, Kentucky, Massachusetts, Maine, Minnesota, Missouri, Northern Mariania Islands, Mississippi, North Carolina, North Dakota, New Jersey, Nevada, South Carolina, Utah, Virginia, Wisconsin, West Virginia and Wyoming.
34
35
36
37