## Weekly Update
No. | Weekly Update Report Data (sheet 1 of 2) Version 1.1
| Agency Name: | Transportation
| Week End Date: | 2009-04-03
| Submitter Name: | Lana Hurdle
| Submitter Contact Info: | 202-366-9191
| Program Source/ Treasury Account Symbol: Agency Code | Program Source/Treasury Account Symbol: Account Code | Program Source/Treasury Account Symbol; Sub-Account Code (OPTIONAL) | Program Description (Account Title) | Total Appropriation | Total Obligations | Total Disbursements
1 | 69 | 1304 | 2009/2010 | Facilities and Equipment, Recovery Act | 200000000 | 0 | 0
2 | 69 | 1306 | 2009/2010 | Grants-in-aid for Airports, Recovery Act | 1100000000 | 4188392 | 0
3 | 69 | 0504 | 2009/2010 | Highway Infrastructure Investment, Recovery Act | 27460000000 | 4994976890.78 | 2115031.09
4 | 69 | 0504 | 2009/2012 | Highway Infrastructure Investment, Recovery Act | 40000000 | 17166.94 | 5596.27
5 | 69 | 0718 | 2009/2014 | Capital Assistance for High Speed Rail Corridors, Recovery Act | 20000000 | 0 | 0
6 | 69 | 0724 | 2009/2010 | Capital Grants to the National Railroad Passenger Corporation, Recovery Act | 1295000000 | 1288536000 | 11000
7 | 69 | 0724 | 2009/2013 | Capital Grants to the National Railroad Passenger Corporation, Recovery Act | 5000000 | 5000000 | 0
8 | 69 | 0718 | 2009/2012 | Capital Assistance for High Speed Rail Corridors, Recovery Act | 7980000000 | 0 | 0
9 | 69 | 1133 | 2009/2010 | Capital Investment Grants, Recovery Act | 742500000 | 0 | 0
10 | 69 | 1102 | 2009/2010 | Fixed Guideway Infrastructure Investment, Recovery Act | 742500000 | 0 | 0
11 | 69 | 1101 | 2009/2010 | Transit Capital Assistance, Recovery Act | 6850700000 | 48616982 | 0
12 | 69 | 1101 | 2009/2012 | Transit Capital Assistance, Recovery Act | 49300000 | 0 | 0
13 | 69 | 1133 | 2009/2012 | Capital Investment Grants, Recovery Act | 7500000 | 0 | 0
14 | 69 | 1102 | 2009/2012 | Fixed Guideway Infrastructure Investment, Recovery Act | 7500000 | 0 | 0
15 | 69 | 1749 | 2009/2010 | Operations and Training, Recovery Act | 2000000 | 0 | 0
16 | 69 | 1771 | 2009/2010 | Assistance to Small Shipyards, Recovery Act | 98000000 | 0 | 0
17 | 69 | 0131 | 2009/2013 | Salaries and Expenses, Recovery Act | 20000000 | 0 | 0
18 | 69 | 0106 | 2009/2011 | Supp Disc Grants for Natl Surface Transport System, Recovery Act | 1500000000 | 0 | 0
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Major Activities
No. | Weekly Update Report Data (sheet 2 of 2)
| Short bulleted list of the major actions taken to date | Short bulleted list of the major planned actions
1 | As of April 3rd, FAA has identified $1,008 million of specific Recovery Act airport projects (94 percent of available total funding). Of that amount, $939 million has been forwarded to DOT for Congressional notification and $681 million have completed the notification process. | During the weeks of April 6 and April 13, FHWA will allocate funds to the National Park Service and Bureau of Indian Affairs for improving roads and bridges within, and providing access to, National Parks and Tribal lands.
2
3 | FAA Office of Airports conducted the following ARRA briefings: March 27, 2009 - Florida Airports Council and March 31, 2009 - National Association of State Aviation Officials (represented by all 50 states’ Directors of Aeronautics) | FHWA aims to finalize its Risk Management Plan by April 6th.
4
5 | As of April 2, FTA has awarded 5 grants for a total obligation of $48.6 million in ARRA funds. In addition, FTA has 72 grant applications totaling $1.2 billion in process to be obligated. | Efforts are underway to identify a potential June 29th event marking the anniversary of President Eisenhower signing the Federal-aid Highway Act of 1956, the start of the interstate highway system.
6
7 | On April 1, FTA hosted a one-day training workshop for regional and headquarters staff aimed at enhancing their knowledge of ARRA programs, requirements, grant development, grant implementation, monitoring and abuse. | FTA will host a webinar on April 8, for approximately 250 potential applicants on the Transit Investments for Greenhouse Gas and Energy Reduction (TIGGER) program.
8
9 | As of April 3, FHWA has authorized 1,531 projects in 42 states, and obligated $4.88 billion. | FTA is coordinating with the Office of the Secretary regarding possible sites for ARRA related events during the “Recovery Tour” scheduled for April 15 - 17th.
10
11 | On March 30, FHWA issued a solicitation for Ferry Boats Discretionary Program. | FRA finalized the FRA the internal draft of the Strategic Plan for high-speed and intercity passenger rail grant programs, and submitted to the Secretary for review. FRA will meet the April 18th deadline.
12
13 | On April 1, FHWA held a teleconference with State CEOs to discuss ARRA risk management plan. | On April 6th, FRA will meet with representatives of the Class I freight railroads and the Association of American Railroads to discuss partnership issues surrounding high-speed rail and intercity passenger rail grant programs
14
15 | On April 2, FHWA allocated the remainder ($5.2 million) of ARRA funds to repair roads and bridges on the Fish and Wildlife Service’s Refuge Road system. | Applications for Small Shipyard Grants are due April 20, 2009; MARAD will announce number of submissions the following day.
16
17 | The Office of Senior Procurement Executive (OSPE) reviewed new draft implementing guidance to determine impact on DOT and is developing a strategy to meet reporting requirements. | DOT Grants Executive Board will hold their first meeting on April 6, 2009. The Board will focus on risk management and vulnerabilities for all DOT financial assistance programs under ARRA.
18
19 | On April 1st, DOT held risk management training for 50 attendees from offices across the Department. OST is coordinating the risk management plan for all DOT programs. The training was the first phase of the plan. | The Jobs Working Group received comments on draft internal guidance, and plan to issue final guidance the week of April 6th. This will help ensure we met the May 18th deadline for reporting jobs data.
20
21 | The week of March 30th, DOT’s help desk handled 40 calls from the public concerning ARRA implementation. | April 6th is the deadline for Operating Administrations to complete the risk assessment questionnaire. OST will now review these questionnaires. Throughout the months of April and May OST will work with Operating Administrations to complete risk profile template, develop a risk mitigation strategy and complete testing and validation of the information.
22
23 | On April 2nd Secretary LaHood was interviewed by David Shepardson of the Detroit News on transportation and ARRA issues. | Efforts are underway to identify a potential event for May 9th in conjunction with “Train Day.” This date commemorates the day the last spike was driven in connecting the First Transcontinental Railroad.
24
25 | On April 2nd Secretary LaHood was interviewed by Miles O'Brien of PBS on transportation and economic recovery issues. | A Town Hall Training Workshop on ARRA for DOT staff will take place the week of April 13th . This training is designed for staff below the management level that may be tasked with implementation tasks yet may not fully understand the special requirements in ARRA.
26
27 | On March 31st, Secretary LaHood was interviewed by the Chicago Tribune for a profile focusing on his contributions to the economic recovery effort. | DOT will complete its section 1609(c) report to CEQ on the status of NEPA compliance for ARRA projects by the April 9th deadline.
28
29 | On April 2nd, Secretary LaHood talked to the Longshoreman & Warehouse Union about transportation and economic recovery.
30
31 | On March 30th, Secretary LaHood spoke at the Council on Access and Mobility Awards Ceremony about economic recovery funds.
32
33 | On April 3rd, DOT Office of General Counsel issued a memorandum and forms on the requirements for transparency of communications with registered lobbyists as outlined in the President’s Memorandum, issued March 20, 2009.
34
35
36
37